## Read me
ZAZEN TAX
Applications and Retentions Tracker
What you applied for, what was certified, what is retained, and when it is due back.
Two debtors, and the smaller one gets all the attention
Everyone knows about retention. Fewer people track the gap between what they applied for and what was actually certified, and on most contracts that gap is larger.
A certificate for less than the application is a disagreement, not an accounting entry. Left alone for three months it becomes a fact.
Retention has two dates and people remember one
Half at practical completion, half at the end of the defects liability period, often a year later. The second one arrives when the job is long finished and nobody is looking at the file.
What this sheet does
One row per application. It totals the certification gap, the retention held, and shows the release dates so the second half is chased rather than remembered.
General information
Rates are those applying in 2026/27 for the UK. This is general information, not advice for your circumstances.

## Applications
ZAZEN TAX
Applied, certified, retained
Yellow is yours.
Contractor | Site | App no | Applied | Certified | Gap | Retention | Net due | First release | Final release
Marchmont Homes | Ellis Way | 1 | 18000 | 18000 |  |  |  | 6 | 18
Marchmont Homes | Ellis Way | 2 | 22000 | 20500 |  |  |  | 6 | 18
Hale Construction | Fell Street | 1 | 31000 | 31000 |  |  |  | 6 | 12
Hale Construction | Fell Street | 2 | 27500 | 24000 |  |  |  | 6 | 12
Oakfield Contracts | Nye Avenue | 1 | 14200 | 14200 |  |  |  | 3 | 12
Verity Build | Camden Row | 1 | 9800 | 8100 |  |  |  | 6 | 18
What is owed to you
Applied for
Certified
Certification gap |  | Applied for and not certified. Argue this now.
Retention held
Total outstanding |  | The gap plus the retention.
The gap as a multiple of the retention |  | Over 1 means the unargued certificates are the bigger problem.
A certificate for less than you applied for is a disagreement. Left three months it becomes a fact.