## Read me
ZAZEN TAX
Project P and L Tracker
Every live project: quote, burn at cost, margin, on one sheet.
The portfolio view
Per project: the fee, budgeted and burned hours at the blended cost rate, external costs, and the margin both planned and landing. Weekly, while each is alive.
The demo
Four projects: the worked £24,000 job landing at 36 per cent, one on budget, one underwater, one just started.
General information
Payroll rates follow the model verified against gov.uk, 2026/27. The metrics are stated management conventions. This is general information, not advice for your circumstances.

## Portfolio
ZAZEN TAX
ZAZEN TAX
Every live job
Blended cost rate | 58
Project | Fee | Budget hrs | Burned | External | Margin | Margin pct | Overburn
Fernwell site | 24000 | 200 | 265 | 0
Loop brand | 15000 | 120 | 118 | 900
Marlin video | 8000 | 90 | 140 | 1200
Piper launch | 30000 | 260 | 40 | 0
The book
Read column H weekly: overburn caught alive is a change order, caught dead it is column F.