## Read me
ZAZEN TAX
Project Profitability Workbook
Quote against burn, at honest cost rates.
Weekly, not post-mortem
Burned hours against budget, while the project is alive, at loaded cost rates. Overburn caught early is a change order; caught late it is a thinner margin.
The demo
£24,000 quoted, 200 hours planned, 265 burned: 51.7 per cent planned, 36 per cent landed.
General information
Payroll rates follow the model verified against gov.uk, 2026/27. The metrics are stated management conventions. This is general information, not advice for your circumstances.

## The project
ZAZEN TAX
ZAZEN TAX
Quote against burn
Fee quoted | 24000
Hours budgeted | 200
Hours burned | 265
Blended cost rate | 58
External costs | 0
The computation
Planned margin
planned percentage
Actual margin
actual percentage
Overburn
Copy this block per project, or use the Project P and L Tracker for the whole portfolio on one sheet.