## Read me
ZAZEN TAX
WIP and Revenue Recognition Workbook
The month-end cut, both directions: earned but unbilled, billed but unearned.
Percentage of completion
Each project's fee times work complete, less what has been billed: positive is accrued income the month earned, negative is deferred income it has not.
The demo
One job 60 per cent done and 40 billed accrues £4,800; another 50 done and 70 billed defers £3,600.
General information
Payroll rates follow the model verified against gov.uk, 2026/27. The metrics are stated management conventions. This is general information, not advice for your circumstances.

## The cut
ZAZEN TAX
ZAZEN TAX
Month end, honestly
Project | Fee | Complete | Billed | WIP
Fernwell site | 24000 | 60% | 40%
Loop brand | 18000 | 50% | 70%
Piper launch | 30000 | 15% | 0%
Net WIP
Reading it
Accrued income, earned unbilled
Deferred income, billed unearned
Percentage complete comes from the project lead against the plan, not from hours spent: burned hours measure cost, not progress. The cut makes the month true and the year end boring.